## Sheet1
PBI | Tasks | Not Started | Initials | Completed (name / date)
As the election official, I want the MPO election to find a winner because the Secretary of State wants that type of election to work Acceptance Criteria: The election counting are fair, The application can generate real winner, Correct winner found, Runs on CSE lab machines Definition of Done: Name of the winner printed out, coding complete, documentation, unit testing, system testing. Effort: Medium PBI Author(s) Max Bryson, Christopher Miao, Ruichen He, Hannah Nelson | Determine Election Type (MPO) |  | HN | Hannah Nelson / 11/29/23 | Steps:
| Process File Header |  | MB | Max Bryson 11/29/23 | MPO election
| Add Vote |  | HN | Hannah Nelson 12/01/23 | Handle MPO file
| Find Winner |  | MB | Max Bryson 12/6/23 | MPO stats to screen, % etc. (not audit files)
| If Tie, find winner with Fair Coin Toss |  | MB | Max Bryson 12/6/23 | IRV ballots
| Print Winner to Screen |  | HN+MB | MB 12/6/2023
| In--Line Documentation |  | MB | Max Bryson 12/6/23
| Doxygen Comments |  | MB | Max Bryson 11/29/23
| Create Unit Tests |  | HN | Hannah Nelson 12/4/23
| Run Unit Testing |  | MB | Max Bryson 12/7/2023
| Create System Tests |  | HN | Hannah Nelson 12/4/23
| Run System Testing |  | MB | Max Bryson 12/7/2023
As the election official, I want to see the vote distribution so I can see how the candidate did. Acceptance Criteria: The MPO stats are printed out to the screen Definition of Done: MPO stats are displayed to the terminal, coding complete, Documentation, and testing complete. Effort: Small PBI Author(s) Max Bryson, Christopher Miao, Ruichen He, Hannah Nelson
| Print intitial vote distribution |  | MB | Max Bryson 12/7/2023
| Print final seats/winners |  | MB | Max Bryson 12/6/2023
| In--Line Documentation |  | MB | Max Bryson 12/6/2023
| Doxygen Comments |  | MB | Max Bryson 12/6/2023
| Create Tests |  | HN | Hannah Nelson 12/4/23
| Run Tests |  | MB | Max Bryson 12/7/2023
As the election official, I don’t want to count the invalid votes, as required by the Secretary of State. Acceptance Criteria: Election finds a correct winner with only valid votes in an unbiased manner. Definition of Done: Election is able to validate the votes, find the winner using only valid votes, coding complete. Documentation and Testing is complete. Effort: Small PBI Author(s): Ruichen He, Max Bryson | Go over each IRV ballot and validate |  | CM | Christopher Miao 12/01/23
| Print out the invalid ballot |  | CM | Christopher Miao 12/01/23
| In-Line Documentation |  | CM | Christopher Miao 12/08/23
| Doxygen Comments |  | CM | Christopher Miao 12/04/23
| Create Unit Tests |  | CM | Christopher Miao 12/08/23
| Run Unit Testing |  | RH | Ruichen He 12/08/2023
| Create System Tests |  | CM | Christopher Miao 12/08/23
| Run System Testing |  | CM | Christopher Miao 12/08/23
As the election official, I want to remove the invalid vote from IRV so I can see which votes are invalid. Acceptance Criteria: Invalid ballots will be removed and stored in an audit file Definition of Done: Show the removed invalid ballots in an audit file, coding complete. Documentation and Testing is complete. Effort: Small PBI Author(s): Ruichen He, Hannah Nelson | Remove the invalid ballot |  | RH | Ruichen He 11/30/23
| Print out the ballot been removed |  | RH | Ruichen He 12/05/23
| In-Line Documentation |  | RH | Ruichen He 12/08/2023
| Doxygen Comments |  | RH | Ruichen He 12/08/2023
| Create Unit Test |  | RH | Ruichen He 12/08/2023
| Run Unit Testing |  | RH | Ruichen He 12/08/2023
| Create System Test |  | RH | Ruichen He 12/08/2023
| Run System Testing |  | RH | Ruichen He 12/08/2023
| Add the remove ballot in the audit file |  | RH | Ruichen He 12/08/2023